## 3. Daily Standup Report (Exampl
Sprint Day | Impediments | Action Taken
Sprint 1 Day 1 | Access to the raw KYC data store was initially denied due to missing security credentials. | Backend lead worked with IT security to obtain and configure the necessary temporary access keys.
Sprint 1 Day 2 | Discovered that the scanned document images (Aadhaar/Bills) had inconsistent resolutions and rotations, impacting initial OCR attempts. | Implemented a dedicated image normalization and pre-processing pipeline (rotation, deskewing) before feeding to OCR.
Sprint 1 Day 3 | The data cleaning script failed repeatedly because certain fields (e.g., date formats) were highly non-standard across different source documents. | Added robust try/except blocks and implemented a regex-based cleaning function to handle various date formats.
Sprint 1 Day 4 | The resulting "clean" dataset volume was too large to store and share efficiently for the data science team. | Implemented Parquet compression for the cleaned data and stored it in a cloud object storage bucket.
Sprint 1 Day 5 | Difficulty in setting up the data validation checks (e.g., verifying address length) due to lack of defined business rules. | Held a quick session with the Product Owner and Compliance Analyst to define the acceptance criteria for cleaned data.
Sprint 2 Day 1 | NLP model training failed due to out-of-memory errors on the assigned GPU instance when processing large text fields. | Switched to a larger GPU instance type and implemented gradient accumulation to train with larger effective batch sizes.
Sprint 2 Day 2 | The CNN model accuracy for document tampering detection was poor (below the required threshold) on the initial test set. | Began hyperparameter tuning and integrated data augmentation techniques (minor distortion, noise) to enrich the training set.
Sprint 2 Day 3 | Difficulty integrating the newly trained GNN model into the common experimentation framework due to its unique dependency requirements. | Created a dedicated, isolated Docker container for the GNN model to manage its specific dependencies.
Sprint 2 Day 4 | The model validation script (T_05) encountered errors because the input features from Sprint 1 were slightly altered during a schema update. | Updated the feature pipeline in the validation script to match the latest Sprint 1 data schema.
Sprint 2 Day 5 | The model accuracy comparison was delayed because the baseline model results were not properly logged during initial runs. | Reran the baseline model with proper MLflow (or similar) logging to accurately track and compare all metrics.
Sprint 3 Day 1 | Integration with backend API not responding | Fixed endpoint mapping in Flask routes
Sprint 3 Day 2 | Fraud detection API taking too long to respond | Optimized model inference time
Sprint 3 Day 3 | Missing AML rules data for testing | Created synthetic AML rule dataset
Sprint 3 Day 4 | API authentication errors | Added JWT-based auth layer
Sprint 3 Day 5 | Everything functional | Proceeded with testing pipeline
Sprint 4 Day 1 | Frontend team is blocked because the required Backend APIs for document upload haven't been deployed to the staging environment yet. | Frontend team shifted focus to finalizing the fraud results visualization components using mock data.
Sprint 4 Day 2 | The DevOps pipeline failed on the deployment step due to missing environment variables for the new GNN model configuration. | DevOps team updated the CI/CD pipeline script to include all necessary environment variables and secrets.
Sprint 4 Day 3 | The frontend dashboard is experiencing cross-origin resource sharing (CORS) errors when attempting to call the Backend API from the user's browser. | Backend team added the Frontend application's domain to the list of allowed origins on the API gateway.
Sprint 4 Day 4 | Performance degradation observed when validating synthetic Aadhaar data (US_05); the full end-to-end latency is too high. | Backend Team identified the OCR extraction module (T_01) as the bottleneck and began optimizing its processing time.
Sprint 4 Day 5 | The visualization of complex fraud results (e.g., GNN linkages) is confusing for compliance analysts in the dashboard prototype. | UX designer held a quick feedback session with the compliance analyst and simplified the visualization to a color-coded risk score.